## DeploymentTracker
Project Northstar deployment tracker
Planned and actual assets by country for the 14-country Meridian Bank rollout.
The actual column is programmatically verified to total exactly 1,870 before this workbook is written.
Country | Planned | Actual | Status | Blocker
Country 01 | 250 | 250 | Complete | None
Country 02 | 220 | 220 | Complete | None
Country 03 | 200 | 200 | Complete | None
Country 04 | 190 | 190 | Complete | None
Country 05 | 180 | 180 | Complete | None
Country 06 | 170 | 170 | Complete | None
Country 07 | 160 | 160 | Complete | None
Country 08 | 155 | 155 | Complete | None
Country 09 | 145 | 145 | Complete | None
Italy | 520 | 0 | Blocked | Regulatory approval pending
Country 11 | 340 | 90 | In progress | Local maintenance window sequencing
Country 12 | 280 | 60 | In progress | Site access batching
Country 13 | 220 | 35 | In progress | Firmware staging queue
Country 14 | 170 | 15 | At risk | Data validation exceptions
Total | 3200 | 1870 | 9 Complete / 5 open | Actual total verified by build script
Control checks
Planned total: 3200
Actual total: 1870
Complete countries: 9
Italy blocker: Regulatory approval pending

## ReadinessNotes
Area | Readiness note | Follow-up
Completed countries | Acceptance evidence has been reviewed and the support handover is operating with standard alert triage. | Keep weekly sampling in place until the next QBR.
Italy | The deployment plan cannot count Italy as available until regulatory approval is confirmed by the customer governance route. | Priya Raman to maintain the evidence pack and escalation log.
In-progress countries | Cutover work is feasible but should remain sequenced around local site access and maintenance windows. | Review the next two cutover windows before moving additional firmware work.
Firmware | The 3.4.2 population is tracked in the status report and should be upgraded only through approved local windows. | Tie each upgrade group to a named country owner.
Reporting evidence | A single evidence template is required so Meridian Bank can compare countries without reformatting the pack. | Rajiv Menon to confirm the acceptance evidence owner.
Customer communication | The tracker should be used as a factual baseline, not as a substitute for the weekly status narrative. | Ava Nakamura to align steering messages with this workbook.
Workbook control
This workbook is generated from the same deployment baseline used in the W-1 status report.
Actual total must remain exactly 1,870 until a new reporting week is generated.
Complete status must remain exactly nine countries for the W-1 package.
No row should be removed from the country list; the total row is a control line, not a country.